STRATEGIC DIRECTIONS 2008-2010

At the October, 2007 retreat of the Board of Governors five areas were broadly identified to define the Strategic Directions for 2008-2010.

- QUALITY – FOCUS ON EXCELLENCE

Emphasis should be on academic health and renewal, development of human resources and facilities improvement.

- DESTINATION COLLEGE – FOCUS ON EXCELLENCE

Emphasis should be on making progress towards establishing St. Clair as a “Destination College”.

- ENROLMENT

Emphasis should be on increasing enrolment, decreasing attrition and introducing new programs.

- COMMUNITY PARTNERSHIPS

Emphasis should be on increasing our positive public image and our community involvement in training especially in the automotive and manufacturing sectors.

- RECREATION CENTRES

Emphasis should be on increasing our student satisfaction numbers by making progress towards construction of the Recreation-Wellness Centres in Chatham and Windsor.

STRATEGIC PLAN 2008-10

This document articulates operational initiatives in five areas.

1.  QUALITY – FOCUS ON EXCELLENCE

Academic Health

- Update of the Academic Strategic Plan, with input from faculty and chairs, which includes an academic planning process and a review of prior plans, the development of a facilities master plan (October 31, 2008) and the following:

  - Strategies specifically on the FCEM to include - 1) assessment of current programs, 2) implementation of two new programs beginning September, 2009 and 3) marketing and recruitment initiatives.

  - Creation of a faculty evaluation model, with full input from students and faculty (March 31, 2009).

  - Selection of new applied degrees to allow for offerings to begin in September, 2010.

  - Develop a Professional Development Program for faculty and academic administration by December 31, 2009.

Academic Renewal

- Ensure all programs have Program Advisory Committees and meetings are held yearly for all programs with Senior Management beginning Fall, 2009.

- Complete two new articulation agreements by September 1, 2008 and another two by September 1, 2009.

Teamwork and Morale

- Perform internal assessment of College needs in human resources for faculty, administration and support staff positions by March 31, 2009.

- Institute an Academic Excellence Award for the 2008 Convocation in June to recognize program excellence.

Facilities Improvement

- Prioritize deferred maintenance items and allocate a minimum of 0.5% of total revenue to reduce unexpected plant costs (September 1, 2008).

- Develop a strategy for the operation of the staff lounge and cafeteria in Windsor by August 31, 2008.

- DESTINATION COLLEGE – FOCUS ON EXCELLENCE

- Initiate the construction of the Centre for Construction, Innovation and Production by March 31, 2009.

- Finalize the configuration of a new Health Science Centre by March 31, 2009.

- Establish a clear position on becoming a polytechnic college (June, 2008).

- Develop a “Chef Star” designation to become a culinary destination College as part of the Academic Strategic Plan (September 1, 2008).

3.	ENROLMENT

- Examine the Health Sciences area by December 31, 2008 to determine new program potential for St. Clair College.

- Introduce a minimum of two new programs at the Thames Campus for Fall, 2009.

- Improve first year enrolment by a minimum of 4% for September, 2008 and an additional 4% for September, 2009.

- Develop and implement a learning success and retention model based on the early identification of at-risk students, early intervention and the provision of appropriate supports and resources.  Increase retention for current students by 1% for Fall, 2008 and an additional 1% for Winter, 2009.

- Present an International Student Enrolment Plan by October 1, 2008.

4.	COMMUNITY PARTNERSHIPS

- Establish greater value to the community manufacturing sector by increasing contract training on new skills development by 10% in each fiscal year.

- Develop mechanisms by August 31, 2008 to initiate St. Clair Days for elementary and high school students in academic and sports competitions during the next school year.

5.	RECREATION CENTRES

- Develop fundraising strategy in 2008-2009 for Recreation – Wellness Centre in Windsor with objective of securing pledges totaling 50% of construction costs by May 1, 2009.

- Develop fundraising strategy in 2008-2009 for Recreation – Wellness Centre in Chatham with objective of securing pledges totaling 50% of construction costs by May 1, 2009.